## Sheet1
Screen: | A
Name: | Distributor List
Purposes: | Description | Navigates to Screen
List distributor with basic data
| Edit button to edit Distributor | B (edit mode)
Remove button to remove Distributor
| Add button to add new Distributor | B (add mode)
| Total Hour Estimate: | 5.5
Screen: | B
Name: | Distributor Information
Purposes: | Description | Navigates to Screen
Add mode: allow new distributor to be saved
Edit mode: allow distributor to be updated
| Branch button: Allow branch list to be updated for individual | E
| T-Reps button: Allow Territory Rep List to be updated | D
| S-Reps button: Allow Service Rep List to be updated | C
| Territory button: allow contracts to be worked on | F
| Total Hour Estimate: | 5
Screen: | C
Name: | Service Rep List
Purposes: | Description | Navigates to Screen
| Add REP button: Load Service Rep Information Screen in "add" mode | H (add mode)
| Edit button: Load Service Rep Information Screen in "edit" mode | H (edit mode)
Remove button: Remove a service rep from the list
List all service reps from the area
| Close button: close the screen and go back to distributor information | B
| Total Hour Estimate: | 4
Screen: | D
Name: | Territory Rep List
Purposes: | Description | Navigates to Screen
| Add REP button: Load Territory Rep Information Screen in "add" mode | I (add mode)
| Edit button: Load Territory Rep Information Screen in "edit" mode | I (edit mode)
Remove button: Remove a Territory rep from the list
List all Territory reps from the area
| Close button: close the screen and go back to distributor information | B
| Total Hour Estimate: | 3
Screen: | E
Name: | Distributor Branch List
Purposes: | Description | Navigates to Screen
List all distributor branches under a given distributor
| Add Branch: Load Branch Information Screen in "add" mode | J (add mode)
| Edit Branch: Load Branch Information Screen in "edit" mode | J (edit mode)
Remove branch button: Remove a branch from a distributor
| Close button: close the screen and go back to previous screen | B or F
| Total Hour Estimate: | 10
Screen: | F
Name: | Territory
Purposes: | Description | Navigates to Screen
Allow drilldown of country, category, state to choose a contract to edit
| Edit button: Load specified contract details in counties form (wizard process) | G (edit mode)
| Cancel : return to Distributor Information screen | B
Next: same as edit. Consolidate these?
| Total Hour Estimate: | 10
Screen: | G
Name: | Counties
Purposes: | Description | Navigates to Screen
List all counties in the state specified on previous screen
Allow update of checked counties list
Cancel : return to Distributor Information screen
| Next: Move to Distributor branch list screen | E
Select All / Deselect All
Edit List button: Edit mode enabled for current list of counties
| Total Hour Estimate: | 10
Screen: | H
Name: | Service Rep Information
Purposes: | Description | Navigates to Screen
Allow update of service rep information
Allow adding of new service rep
| Cancel: return to service rep list | C
Save: Save the list
| Total Hour Estimate: | 3.5
Screen: | I
Name: | Territory Rep Information
Purposes: | Description | Navigates to Screen
Allow update of territory rep information
Allow adding of new territory rep
| Cancel: return to territory rep list | D
Save: Save the list
| Total Hour Estimate: | 2
Screen: | J
Name: | Branch Information
Purposes: | Description | Navigates to Screen
Allow udate of branch information
Allow adding of new branch to distributor
| Cancel: Return to Distributor Branch List | E
| Save: Save the information and return to Distributor Branch List | E
| Total Hour Estimate: | 4
Screen: | K
Name: | Contract Information
Purposes: | Description | Navigates to Screen
Allow editing of contract date
| Cancel: Return to Distributor Branch List | E
| Save: Save the information and return to Distributor Branch List | E
| Total Hour Estimate: | 2.5
Screen: | L, M, N, O
Name: | Distributor Branch List, Territory, Counties, Contract Information
Purposes: | Same as screens E, F, G, K
| Total Hour Estimate: | Included in screens E, F, G, K
| Task | Hours
| Overall Total Hours for Form Creation + QA: | 57.5
| Database Schema + Construction: | 7
| Deployment: | 3
| Total: | 67.5
| Rate (per hour): | 40
| Total Cost: | 2700
*Note: Hour total does not include reports